## Sheet1
SR# | Project | platform | Plan | Ver | developer name | QA Name | Task | Description | Start date | End date | Task Status | Test Cases | Blocker | Major | Med | Defects Count | Reopen/Fixes Count | Build Status
1 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108824 | add news letter functionality | 2025-06-16 | 2025-06-20 | QA Verified | 14 | 0 | 0 | 0 | 0 | 0 | ready to live
2 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108825 | add news section in website | 2025-06-16 | 2025-06-20 | QA Verified | 10 | 0 | 0 | 0 | 0 | 0 | ready to live
3 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108855 | add slider functionality. | 2025-06-16 | 2025-06-20 | QA Verified | 14 | 1 | 0 | 1 | 2 | 1 | ready to live
4 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108927 | create about us page | 2025-06-16 | 2025-06-20 | QA Verified | 7 | 0 | 0 | 0 | 0 | 0 | ready to live
5 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108954 | Add language Feature | 2025-06-16 | 2025-06-20 | QA Verified | 5 | 0 | 0 | 1 | 1 | 1 | ready to live
6 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111100 | sevices section on home page and separate page | 2025-06-16 | 2025-06-20 | QA Verified | 6 | 0 | 0 | 0 | 0 | 0 | ready to live
7 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111122 | update donate Now screen. | 2025-06-16 | 2025-06-20 | QA Verified | 2 | 0 | 0 | 0 | 0 | 0 | ready to live
8 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111130 | create dynamic funtionality for contact us | 2025-06-16 | 2025-06-20 | QA Verified | 5 | 0 | 0 | 1 | 0 | 0 | ready to live
9 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111560 | add translation for static content | 2025-06-16 | 2025-06-20 | QA Verified | 1 | 0 | 0 | 0 | 0 | 0 | ready to live
10 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111746 | set theme color scheme | 2025-06-16 | 2025-06-20 | QA Verified | 1 | 0 | 0 | 0 | 0 | 0 | ready to live
11 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109049 | Create upcoming Event section | 2025-06-16 | 2025-06-20 | QA Verified | 3 | 0 | 0 | 0 | 0 | 0 | ready to live
12 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109050 | Create Events management module for admin | 2025-06-16 | 2025-06-20 | QA Verified | 6 | 0 | 0 | 0 | 0 | 0 | ready to live
13 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109051 | create a galley page | 2025-06-16 | 2025-06-20 | QA Verified | 3 | 0 | 0 | 0 | 0 | 0 | ready to live
14 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109052 | create galley management module for admin | 2025-06-16 | 2025-06-20 | QA Verified | 7 | 0 | 0 | 0 | 0 | 0 | ready to live
15 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109499 | create video gallery module in admin side | 2025-06-16 | 2025-06-20 | QA Verified | 9 | 0 | 0 | 1 | 0 | 1 | ready to live
16 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109331 | create document uploading module | 2025-06-16 | 2025-06-20 | QA Verified | 8 | 0 | 0 | 0 | 0 | 0 | ready to live
17 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 110800 | add functionality about media gellery=> decuments | 2025-06-16 | 2025-06-20 | QA Verified | 5 | 0 | 0 | 0 | 0 | 0 | ready to live
18 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 109464 | Create module for Add Mubaligh | 2025-06-16 | 2025-06-20 | QA Verified | 3 | 1 | 0 | 0 | 1 | 1 | ready to live
19 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 110665 | create organizational module admin and user side. | 2025-06-16 | 2025-06-20 | QA Verified | 10 | 0 | 0 | 0 | 0 | 0 | ready to live
20 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111593 | Create module for tanzeemi location in NEW ORG website | 2025-06-16 | 2025-06-20 | QA Verified | 4 | 0 | 0 | 0 | 0 | 0 | ready to live
21 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111741 | department integration with PMS software | 2025-06-16 | 2025-06-20 | QA Verified | 14 | 0 | 0 | 1 | 1 | 1 | in development
22 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111742 | display department with department Hierarchy in department page | 2025-06-16 | 2025-06-20 | QA Verified | 8 | 0 | 0 | 0 | 0 | 0 | ready to live
23 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111131 | create dynamic page for rukn shoora. | 2025-06-16 | 2025-06-20 | QA Verified | 8 | 0 | 0 | 0 | 0 | 0 | ready to live
24 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111743 | integration rukn shoora profile with department. | 2025-06-16 | 2025-06-20 | QA Verified | 3 | 0 | 0 | 0 | 0 | 0 | ready to live
25 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108732 | implamentation of new theme for org website | 2025-06-16 | 2025-06-20 | QA Verified | 1 | 0 | 0 | 0 | 0 | 0 | ready to live
26 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108739 | create footer section in new org theme | 2025-06-16 | 2025-06-20 | QA Verified | 6 | 0 | 0 | 0 | 0 | 0 | ready to live
27 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111745 | Login page ..data setup on login page | 2025-06-16 | 2025-06-20 | QA Verified | 6 | 0 | 0 | 0 | 1 | 1 | ready to live
28 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111935 | add introduction founder of Dawateislami | 2025-06-16 | 2025-06-20 | QA Verified | 4 | 0 | 0 | 1 | 1 | 1 | ready to live
29 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 111936 | add introduction caliph of ameer e ahle sunnat | 2025-06-16 | 2025-06-20 | QA Verified | 5 | 0 | 0 | 0 | 0 | 0 | ready to live
30 | Dawateislami.ORG | web | QA Plan | 4 | Usman Diljan | Adnan Yousaf | 108732 | SSO org dashboard user integration | 2025-06-16 | 2025-06-20 | QA Verified | 5